## Sheet1
Date | Work | Assignment due
11/13 | Complete proposal | 11/13, 1pm
11/16-11/19 | Project review meeting with TA | 11/16-11/19
11/20-11/21 | Complete data collection and division of labor | NA
11/21-11/26 | Individual data analysis | NA
11/27 | Group meeting: discuss everyone’s work and any problems | NA
11/28-12/3 | Individual work | NA
12/4-12/7 | Webpage design and screencast | 12/11, 4PM
12/7-12/10 | Group meeting: finalize report | NA
12/11 | Complete report | 12/11, 4PM
12/11 | Peer assessment | 12/11, 8PM